## Defect Response
Defect ID | Title | Module | Severity | Customer Status | Resolution Status | Remarks / Resolution Detail | Code Path / Files | QA Verification Steps
PPA-1 | Login - Invalid credentials shows blank page | Authentication | High | Failed | Already Resolved | Closed in earlier remediation cycle (TCID-LOGIN-005). LoginPage.js now does a client-side email regex pre-check, the form has `noValidate`, and the catch block ALWAYS shows a sonner toast and stays on the page (never navigates on error). | /app/frontend/src/pages/LoginPage.js (handleLogin) | Try login with malformed email (e.g. 'foo') OR unknown email + valid password — expect toast + form remains visible.
PPA-14 | Vehicle Management - cannot prevent delete with active booking | Vehicle Management | High | Failed | Resolved | DELETE /api/vehicles/{id} now refuses to delete when the vehicle has any reservation in {pending, confirmed} with date >= today, returning 400 'Cannot delete vehicle — it has an active reservation on YYYY-MM-DD'. Past reservations no longer block deletion. | /app/backend/routes/vehicles.py (delete_vehicle) | 1) Create vehicle V; 2) Create future reservation using V; 3) Attempt DELETE /api/vehicles/V → expect 400; 4) Cancel reservation → DELETE succeeds.
PPA-15 | Building names not aligned in Reservations by Buildings graph | Admin Dashboard | Low | Failed | Already Resolved | Closed in QAT round (TCID-DASHBOARD-008). YAxis widened to 180px with interval={0} and a tickFormatter that truncates with ellipsis; full name preserved in the recharts Tooltip. | /app/frontend/src/pages/admin/AdminDashboard.js (BarChart YAxis) | Reload Admin Dashboard with at least 4 buildings of varying name lengths — labels should not overlap or be clipped.
PPA-17 | User Dashboard - tooltip overlaps page title | User Dashboard | Low | Failed | Resolved | Universal fix on the shadcn TooltipContent component: now passes collisionPadding={16} and avoidCollisions=true so tooltips automatically flip side when near the page edge / sticky header. Applies to every tooltip in the app. | /app/frontend/src/components/ui/tooltip.jsx | Hover any info icon near the top of any page — tooltip should flip downward instead of overlapping the header.
PPA-19 | Daily Reservations chart - dates jumbled / unsorted | Reports & Analytics | Medium | Failed | Resolved | Backend /api/reports/stats now returns daily_breakdown sorted ascending by date. Verified via curl — dates come out in chronological order. | /app/backend/routes/reports.py (line 91) | GET /api/reports/stats and check daily_breakdown[].date is monotonically increasing.
PPA-22 | Building Management - slot color does not change to gray when reservation is created | Building Management | High | Failed/Blocked | Already Resolved | Closed in QAT round (TCID-BUILDING-MANAGEMENT-027). BuildingManagement.js refetches on window focus, on document visibilitychange, and every 30 seconds while the tab is visible. Slot colors update without F5. | /app/frontend/src/pages/admin/BuildingManagement.js | Open Building Management in tab A; create reservation in tab B; switch back to tab A — slot color flips from green to gray within 1 second of focus.
PPA-24 | Disconnect between Reservations by Buildings graph and slot statuses | Reports & Analytics | Medium | Failed | Verify Deploy | Same root cause as PPA-22 (data freshness). The polling/focus refetch from PPA-22 + the newest-first reservations sort from PPA-57/TCID-ANALYTICS-016 mean the graph and the slot grid now reconcile within 30 seconds. If the QA observation persists post-deploy, the next likely cause is a CDN/edge cache — invalidate and retest. | /app/frontend/src/pages/admin/Reports.js, /app/frontend/src/pages/admin/BuildingManagement.js | Create a reservation; within 30 s reload Reports + Building Management — both should reflect the new booking.
PPA-30 | User does not receive email notifications for waitlist / reservation events | Notifications | Medium | Failed | Backlog (P1) | Email notifications for waitlisted users + reservation events is an explicit P1 future task in PRD.md. Backend currently writes in-app notifications. Bringing this to GA needs an SMTP/Resend/SendGrid integration (recommend Resend or Emergent SMTP). Not in scope for this defect cycle. | Future: /app/backend/services/email.py (TBD) | Out of scope for this validation cycle. Item is tracked in PRD.md backlog.
PPA-31 | Save button hidden under 'Made with Emergent' badge | Admin Settings | Medium | Failed | Resolved | AdminLayout main content area now has pb-24/pb-28 (96px / 112px bottom padding). The platform's floating Emergent badge always sits in the bottom-right; this guarantees Save / submit buttons don't get covered. | /app/frontend/src/pages/admin/AdminLayout.js (line 154-157) | Open AdminSettings on a viewport ≥ md and verify the Save button is fully clickable; the badge no longer overlaps.
PPA-54 | Reports - date picker only allows changing END date | Reports & Analytics | Medium | Failed | Already Resolved | Closed in QAT round (TCID-ANALYTICS-004). Calendar's onSelect now commits any non-null change immediately — single click works as a same-day range; second click extends or restarts the range. | /app/frontend/src/pages/admin/Reports.js (Calendar onSelect) | Open Reports → date picker → click any single date → it should be accepted as both start and end. Click another date → range expands.
PPA-57 | Recent Reservations table shows stale data | Reports & Analytics | Medium | Failed | Already Resolved | Closed in QAT round (TCID-ANALYTICS-016). Reports.js now sorts client-side by created_at DESC and refetches on focus / visibility change. Recent Reservations always shows the latest activity. | /app/frontend/src/pages/admin/Reports.js (fetchReservations + useEffect) | Create a reservation; switch to Reports tab → it should appear at the top of Recent Reservations within 1 second of focus.
PPA-58 | User Management - tooltip overlaps with header | User Management | Low | Failed | Resolved | Same universal fix as PPA-17. shadcn TooltipContent now uses Radix collisionPadding=16 and avoidCollisions=true. | /app/frontend/src/components/ui/tooltip.jsx | Hover the User Management header tooltip — it should flip downward instead of clashing with the page title.
PPA-59 | Block Slots dialog - only first conflicting slot reported | Event Blocking | Medium | Failed | Already Resolved | Closed in QAT round (TCID-EVENT-BLOCKING-012). create_event_block now does a two-pass create: collect ALL conflicting slots in pass 1, raise once with the full comma-separated list, only insert in pass 2 if pass 1 was empty. | /app/backend/routes/event_blocks.py (create_event_block) | POST /api/event-blocks with 3 slot_ids that all conflict on the same date — error detail must list all 3 slot labels.
PPA-62 | Booking - able to cancel past reservations | Reservations | Medium | Failed | Resolved | PUT /api/reservations/{id}/cancel now refuses if reservation date is strictly before today; returns 400 'Cannot cancel a past reservation'. Today's reservations remain cancelable. Verified via curl. | /app/backend/routes/reservations.py (cancel_reservation, lines ~292-307) | Pick a reservation with date < today, status in {pending, confirmed} → PUT /cancel returns 400.
PPA-64 | Building Management - slot label / status overlap | Building Management | Low | Failed | Verify (UI) | Slot label rendering already uses `truncate` + `max-w-full` and a `title` attribute — so overflow gets ellipsis with full label on hover. If QA still sees overlap on a specific viewport, share screen size and we'll add a stricter min-width on the badge cluster. | /app/frontend/src/pages/admin/BuildingManagement.js (lines 500-503) | Test on viewports ≥ 1280px and < 768px. Report any specific overlap with a screenshot.
PPA-65 | Building Management - 'Active' character-limit indicator behavior | Building Management | Low | Failed | Already Resolved | Closed in earlier QAT cycle. Phase 6 added explicit maxLength on building text inputs; PUT now uses a permissive BuildingUpdate so legacy buildings round-trip without 422 (TCID-BUILDING-MANAGEMENT-010). | /app/backend/models/building.py, /app/frontend/src/pages/admin/BuildingManagement.js | Try editing a legacy building whose name exceeds 30 chars — PUT should succeed; new buildings still constrained.
PPA-66 | Waitlist - Join Waitlist UX missing from booking flow | Waitlist | Medium | Failed | Verify (UI) | Backend /api/waitlist endpoints all exist and were tested 14/14 in earlier cycles. The Join Waitlist button is rendered conditionally in BookingPage when slots are full and the building has waitlist_enabled=true. If QA cannot see it, confirm waitlist_enabled is true on the building's parking_config. | /app/backend/routes/waitlist.py, /app/frontend/src/pages/BookingPage.js | 1) Set parking_configs.waitlist_enabled=true for the building; 2) Fully book all slots for a date; 3) Try to book → 'Join Waitlist' option should appear.
PPA-14b | Reset User's Main Building - 'Building not found' error | User Management | Medium | Failed | Cannot Reproduce | Could not reproduce on current build — PUT /api/users/{id} accepts main_building=null and assigned_buildings=[] cleanly in our smoke test. Likely an artifact of stale frontend state OR the user's current main_building no longer exists in DB. Recommend QA re-test on freshly deployed build and capture the exact request payload + response. | /app/backend/routes/users.py (update_user) | Re-run with browser DevTools network tab open and capture the failing PUT request body + 4xx response.
PPA-14c | Block a slot from Building Management - status overlaps with name | Building Management | Low | Failed | Verify (UI) | Same as PPA-64 — slot rendering uses truncate. Need a screenshot at a specific viewport size to reproduce. | /app/frontend/src/pages/admin/BuildingManagement.js | Reproduce with screenshot + viewport width.
PPA-14d | View Admin's Dashboard (duplicate row, no detail) | Admin Dashboard | — | Failed | Cannot Reproduce | Row in source spreadsheet had no Title or Actual Result populated — appears to be a duplicate / data-entry artifact. Need QA to specify what was being validated. | — | Please clarify the test scenario; row is currently empty.
PPA-14e | View Admin's Dashboard (duplicate row, no detail) | Admin Dashboard | — | Failed | Cannot Reproduce | Same as above — duplicate empty row. | — | Please clarify the test scenario; row is currently empty.

## Summary
Defect Validation — Response Summary
Source: 'Parking App - Defect Validation.xlsx' ¦ Generated April 28, 2026
Total customer-reported defect rows | 21
Resolution status breakdown
Resolved | 6
Already Resolved | 7
Verify Deploy | 1
Verify (UI) | 3
Backlog (P1) | 1
Cannot Reproduce | 3
Open | 0
Items genuinely resolved this cycle (new code)
PPA-14 — Vehicle Management - cannot prevent delete with active booking | High
PPA-17 — User Dashboard - tooltip overlaps page title | Low
PPA-19 — Daily Reservations chart - dates jumbled / unsorted | Medium
PPA-31 — Save button hidden under 'Made with Emergent' badge | Medium
PPA-58 — User Management - tooltip overlaps with header | Low
PPA-62 — Booking - able to cancel past reservations | Medium