## Defect Response
Defect ID | Title | Module | Severity | Customer Status | Resolution Status | Remarks / Resolution Detail | Code Path / Files | QA Verification Steps
PPA-1 | Login - Invalid credentials shows blank page | Authentication | High | Failed | Already Resolved | Closed in earlier remediation cycle. LoginPage.js does a client-side email regex pre-check, the form has noValidate, and the catch block ALWAYS shows a sonner toast and stays on the page. | /app/frontend/src/pages/LoginPage.js (handleLogin) | Try login with malformed email OR unknown email + valid password — expect toast + form remains visible.
PPA-14 | Vehicle Management - cannot prevent delete with active booking | Vehicle Management | High | Failed | Resolved | DELETE /api/vehicles/{id} now refuses when the vehicle has any reservation in {pending, confirmed} with date >= today, returning 400 'Cannot delete vehicle — it has an active reservation on YYYY-MM-DD'. | /app/backend/routes/vehicles.py (delete_vehicle) | 1) Create vehicle V; 2) Create future reservation using V; 3) DELETE /api/vehicles/V → expect 400; 4) Cancel reservation → DELETE succeeds.
PPA-15 | Building names not aligned in Reservations by Buildings graph | Admin Dashboard | Low | Failed | Already Resolved | YAxis widened to 180px with interval={0} and a tickFormatter that truncates with ellipsis; full name preserved in the recharts Tooltip. | /app/frontend/src/pages/admin/AdminDashboard.js (BarChart YAxis) | Reload Admin Dashboard with at least 4 buildings of varying name lengths — labels should not overlap or be clipped.
PPA-17 | User Dashboard - tooltip overlaps page title | User Dashboard | Low | Failed | Resolved | Universal fix on the shadcn TooltipContent component — collisionPadding={16}, avoidCollisions=true. Tooltips now flip side near the page edge / sticky header. | /app/frontend/src/components/ui/tooltip.jsx | Hover any info icon near the top of any page — tooltip should flip downward instead of overlapping the header.
PPA-19 | Daily Reservations chart - dates jumbled / unsorted | Reports & Analytics | Medium | Failed | Resolved | Backend /api/reports/stats now returns daily_breakdown sorted ascending by date. | /app/backend/routes/reports.py (line 91) | GET /api/reports/stats and check daily_breakdown[].date is monotonically increasing.
PPA-22 | Building Management - slot color does not change to gray when reservation is created | Building Management | High | Failed/Blocked | Already Resolved | BuildingManagement.js refetches on window focus, document visibilitychange, and every 30 s while the tab is visible. Slot colors update without F5. | /app/frontend/src/pages/admin/BuildingManagement.js | Open Building Management in tab A; create reservation in tab B; switch back — slot color flips from green to gray within 1 s of focus.
PPA-24 | Disconnect between Reservations by Buildings graph and slot statuses | Reports & Analytics | Medium | Failed | Verify Deploy | Same root cause as PPA-22 (data freshness). Polling/focus refetch from PPA-22 + newest-first reservations sort from PPA-57 mean the graph and slot grid reconcile within 30 s. If observation persists post-deploy, invalidate CDN/edge cache. | /app/frontend/src/pages/admin/Reports.js, /app/frontend/src/pages/admin/BuildingManagement.js | Create a reservation; within 30 s reload Reports + Building Management — both should reflect the new booking.
PPA-30 | User does not receive email notifications for waitlist / reservation events | Notifications | Medium | Failed | Backlog (P1) | Email notifications is an explicit P1 future task. Backend currently writes in-app notifications + has notify_next_waitlisted_user hooks. Bringing this to GA needs an SMTP/Resend/SendGrid integration. Not in scope for this defect cycle. | Future: /app/backend/services/email.py (TBD) | Out of scope for this validation cycle. Item is tracked in PRD.md backlog.
PPA-31 | Save button hidden under 'Made with Emergent' badge | Admin Settings | Medium | Failed | Resolved | AdminLayout main content area now has pb-24/pb-28 (96 / 112 px bottom padding). Floating Emergent badge no longer covers Save / submit buttons. | /app/frontend/src/pages/admin/AdminLayout.js (lines 154-157) | Open AdminSettings on a viewport ≥ md and verify the Save button is fully clickable; the badge no longer overlaps.
PPA-54 | Reports - date picker only allows changing END date | Reports & Analytics | Medium | Failed | Resolved | DEEPER FIX (2026-04-29): The earlier QAT round only handled half-range clicks. Customer screenshot showed a residual bug — clicking INSIDE an already-complete range made react-day-picker emit onSelect(undefined), dropping the click. Replaced the single mode='range' Calendar with TWO separate mode='single' pickers (Start / End). Every click commits immediately. Cross-validation: a Start after current End auto-pushes End forward; End picker disables dates before Start. | /app/frontend/src/pages/admin/Reports.js (lines 286-336) | Open Reports → click Start: pick any date → button label updates immediately. Click End: pick any date ≥ Start → updates. Stats refetch on each change.
PPA-57 | Recent Reservations table shows stale data | Reports & Analytics | Medium | Failed | Already Resolved | Reports.js sorts client-side by created_at DESC and refetches on focus / visibility change. Recent Reservations always shows the latest activity. | /app/frontend/src/pages/admin/Reports.js (fetchReservations + useEffect) | Create a reservation; switch to Reports tab → it should appear at the top of Recent Reservations within 1 s of focus.
PPA-58 | User Management - tooltip overlaps with header | User Management | Low | Failed | Resolved | Same universal fix as PPA-17 — shadcn TooltipContent uses Radix collisionPadding=16 and avoidCollisions=true. | /app/frontend/src/components/ui/tooltip.jsx | Hover the User Management header tooltip — it should flip downward instead of clashing with the page title.
PPA-59 | Block Slots dialog - only first conflicting slot reported | Event Blocking | Medium | Failed | Already Resolved | create_event_block does a two-pass create: collect ALL conflicting slots in pass 1, raise once with the full comma-separated list, only insert in pass 2 if pass 1 was empty. | /app/backend/routes/event_blocks.py (create_event_block) | POST /api/event-blocks with 3 slot_ids that all conflict on the same date — error detail must list all 3 slot labels.
PPA-62 | Booking - able to cancel past reservations | Reservations | Medium | Failed | Resolved | DEEPER FIX (2026-04-29): Earlier round only fixed user-side endpoint. Customer screenshot showed Admin Reservations UI still rendered Cancel button on past rows AND the admin cancel endpoint had no guard. Added the same past-date guard to PUT /api/admin/reservations/{id}/cancel (returns 400 'Cannot cancel a past reservation') AND the AdminReservations table now hides Cancel for any row with date < today. Both endpoints + UI verified. | /app/backend/routes/users.py (admin_cancel_reservation), /app/backend/routes/reservations.py (cancel_reservation), /app/frontend/src/pages/admin/AdminReservations.js (canCancel) | Pick a past reservation in {pending, confirmed}: 1) PUT /api/admin/reservations/{id}/cancel → 400; 2) PUT /api/reservations/{id}/cancel → 400; 3) AdminReservations table — Cancel button NOT shown.
PPA-64 | Building Management - slot label / status overlap | Building Management | Low | Failed | Verify (UI) | Slot label rendering uses truncate + max-w-full and a title attribute — overflow gets ellipsis, full label on hover. If overlap persists at a specific viewport, share screen size. | /app/frontend/src/pages/admin/BuildingManagement.js (lines 500-503) | Test on viewports ≥ 1280 px and < 768 px. Report any specific overlap with a screenshot.
PPA-65 | Building Management - 'Active' character-limit indicator behavior | Building Management | Low | Failed | Already Resolved | Phase 6 added explicit maxLength on building text inputs; PUT now uses a permissive BuildingUpdate so legacy buildings round-trip without 422. | /app/backend/models/building.py, /app/frontend/src/pages/admin/BuildingManagement.js | Try editing a legacy building whose name exceeds 30 chars — PUT should succeed; new buildings still constrained.
PPA-66 | Waitlist - Join Waitlist UX missing from booking flow | Waitlist | Medium | Failed | Resolved | DEEPER FIX (2026-04-29): Customer reported waitlist still didn't surface even with waitlist_enabled=true. Three real bugs were blocking the flow: (1) /api/parking-config public response was hiding waitlist_enabled (V-02 fix had overcorrected) → BookingPage saw config.waitlist_enabled=undefined and never rendered the banner. Fixed: ParkingConfigPublicResponse now exposes UX flags (waitlist_enabled, no_show_release_*, main_building_exclusive); admin-only operational tuning kept hidden. (2) /api/slots/available ignored event_blocks → all 8 Floor-2 slots looked 'available' so allSlotsFullyBooked never fired. Fixed: get_available_slots merges event_blocks into the hourly timeline, returns is_event_blocked + reason. (3) Couchbase abstraction's find_one() didn't accept sort kwarg, but routes/waitlist.py uses it to compute the next queue position → POST /waitlist/join returned 500 on Couchbase backend. Fixed: find_one(filter, projection, sort) now mirrors Motor's signature. | /app/backend/models/parking_config.py, /app/backend/routes/parking_config.py, /app/backend/routes/buildings.py, /app/backend/database/couchbase_db.py | 1) Set parking_configs.waitlist_enabled=true; 2) Block all slots for a date (event block + reservations); 3) Open BookingPage as a non-admin user → 'All slots are fully booked / Join Waitlist' banner appears; 4) Click Join → toast + Position #1 badge; 5) Leave → toast + Join button reappears.
NEW-EVT-BLOCK | Block Slots dialog does not show existing event-block status | Event Blocking | Medium | Found in re-test | Resolved | NEW FIX (2026-04-29): Customer screenshot showed admin opening Block Slots dialog while another event block was already in effect — slots already taken by the existing block were rendered as green Available (admins could double-block). Fixed by surfacing is_event_blocked + event_block_reason from /api/slots/available; EventBlocking dialog now renders blocked slots in amber with 'Blocked' sublabel, disabled selection, and reason as tooltip. Added 'Event Blocked' to the legend. | /app/backend/routes/buildings.py (get_available_slots), /app/frontend/src/pages/admin/EventBlocking.js | 1) Create event block on slots [9, 10, 11] for a date; 2) Open Block Slots dialog for the same building/floor/date; 3) Slots 9, 10, 11 should render amber, label 'Blocked', tooltip = original reason, disabled.
PPA-14b | Reset User's Main Building - 'Building not found' error | User Management | Medium | Failed | Cannot Reproduce | Could not reproduce on current build — PUT /api/users/{id} accepts main_building=null and assigned_buildings=[] cleanly. Likely stale frontend state OR the user's current main_building no longer exists. Recommend re-test on freshly deployed build with the exact failing payload captured. | /app/backend/routes/users.py (update_user) | Re-run with browser DevTools network tab open and capture the failing PUT request body + 4xx response.
PPA-14c | Block a slot from Building Management - status overlaps with name | Building Management | Low | Failed | Verify (UI) | Same as PPA-64 — slot rendering uses truncate. Need a screenshot at a specific viewport size to reproduce. | /app/frontend/src/pages/admin/BuildingManagement.js | Reproduce with screenshot + viewport width.
PPA-14d | View Admin's Dashboard (duplicate row, no detail) | Admin Dashboard | — | Failed | Cannot Reproduce | Row in source spreadsheet had no Title or Actual Result populated — appears to be a duplicate / data-entry artifact. Need QA to specify what was being validated. | — | Please clarify the test scenario; row is currently empty.
PPA-14e | View Admin's Dashboard (duplicate row, no detail) | Admin Dashboard | — | Failed | Cannot Reproduce | Same as above — duplicate empty row. | — | Please clarify the test scenario; row is currently empty.

## Summary
Defect Validation — Response Summary (v2)
Source: 'Parking App - Defect Validation.xlsx' ¦ Generated April 29, 2026
v2 supersedes the 2026-04-28 file. Rows PPA-54, PPA-62, PPA-66 were upgraded after the customer's screenshot follow-ups exposed deeper bugs that the first-pass fixes had missed. NEW-EVT-BLOCK was added during re-testing.
Total customer-reported defect rows + 1 new finding | 22
Resolution status breakdown
Resolved | 9
Already Resolved | 6
Verify Deploy | 1
Verify (UI) | 2
Backlog (P1) | 1
Cannot Reproduce | 3
Open | 0
Items genuinely resolved this cycle (new code)
PPA-14 — Vehicle Management - cannot prevent delete with active booking | High
PPA-17 — User Dashboard - tooltip overlaps page title | Low
PPA-19 — Daily Reservations chart - dates jumbled / unsorted | Medium
PPA-31 — Save button hidden under 'Made with Emergent' badge | Medium
PPA-54 — Reports - date picker only allows changing END date | Medium
PPA-58 — User Management - tooltip overlaps with header | Low
PPA-62 — Booking - able to cancel past reservations | Medium
PPA-66 — Waitlist - Join Waitlist UX missing from booking flow | Medium
NEW-EVT-BLOCK — Block Slots dialog does not show existing event-block status | Medium
Deeper fixes shipped after customer follow-up (2026-04-29):
PPA-54 — Range picker swapped for two single-date pickers (every click commits).
PPA-62 — Admin cancel endpoint + UI Cancel button now both block past dates.
PPA-66 — Three bugs unblocked the Join Waitlist flow (config field hiding + event_block availability + Couchbase find_one sort).
NEW-EVT-BLOCK — Block Slots dialog now flags slots already covered by another event block.