## Defect Response (2026-04-30)
Defect ID | Title | Severity | Customer Status | Our Assessment | Resolution Status | Remarks / Resolution Detail | Code Path / Files | QA Verification Steps
PPA-1 | Login - Invalid credentials shows blank page | High | Closed | Already fixed | Verified Closed | Spot-checked on this build: POST /api/auth/login with wrong creds returns HTTP 401 + JSON {"detail":"Invalid credentials"} as designed; LoginPage catches and shows a sonner toast, page does not blank. Stays Closed. | /app/frontend/src/pages/LoginPage.js (handleLogin) | POST a malformed/wrong login payload — expect 401 + on-page toast.
PPA-71 | Event Blocking accepts past dates | Medium | Failed (NEW) | Confirmed real | Resolved | REPRODUCED on this build: POST /api/event-blocks with date=2026-03-15 (past) returned HTTP 200 and created the block. Admin should not be allowed to schedule a block in the past. FIX: Added a past-date guard in routes/event_blocks.py (after the date-format check). Today is still permitted (admins occasionally need to retroactively close out the rest of the current day); strictly past dates now return HTTP 400 "Cannot create an event block on a past date". VERIFIED: past date → 400; today (control) → 200. | /app/backend/routes/event_blocks.py (create_event_block) | 1) POST /api/event-blocks with date=<yesterday> → expect 400 with the exact message; 2) POST with date=<today> → expect 200; 3) UI: open Block Slots dialog and try to type a past date → backend now rejects (UI-side guard recommended as a follow-up to disable past dates in the date picker).
PPA-15 | Reservations by Buildings — building names alignment | Low | Closed | Already fixed | Verified Closed | Spot-checked: AdminDashboard BarChart YAxis is width=180 with interval=0 + ellipsis tickFormatter; Tooltip shows the full name. Stays Closed. | /app/frontend/src/pages/admin/AdminDashboard.js (BarChart YAxis) | Reload Admin Dashboard with ≥ 4 buildings of varying name lengths — labels should not overlap or clip.
PPA-70 | User can book reservations outside their assigned zone | High | Failed (NEW) | Confirmed real | Resolved | REPRODUCED: user.test (Main Zone, includes 3 buildings) successfully POSTed /api/reservations for KHO (in 'Head Office Central' zone) → HTTP 200. Should have been 403. ROOT CAUSE: The zone check in routes/reservations.py (`{"user_ids": uid}`) uses MongoDB's implicit ARRAY-MEMBERSHIP semantic — Mongo treats `{field: x}` as "x is one of the elements when field is an array". The Couchbase abstraction in database/couchbase_db.py was translating that to a plain `field = $p`, which always returned false against an array column. Result: on Couchbase, every user appeared to have ZERO zones → check was skipped → users could book anywhere. Same silent failure would also affect any other `{array_field: scalar}` query (assigned_buildings, slot_ids, tags, etc.). FIX: _condition() in couchbase_db.py now emits `(\`field\` = $p OR $p IN \`field\`)`. The OR-right is the N1QL idiom for array membership; the OR-left preserves scalar semantics. Drop-in compatible for both shapes. VERIFIED: cross-zone booking → 403 "You are not assigned to this building's zone"; in-zone booking → permitted (only blocked by orthogonal vehicle-sticker rule). | /app/backend/database/couchbase_db.py (_N1qlBuilder._condition), /app/backend/routes/reservations.py (zone check) | 1) Pick a user assigned to Zone A (which contains Building X but not Building Y); 2) POST /api/reservations for a slot in Building Y → expect 403; 3) POST for a slot in Building X → expect success (or fail only for orthogonal reasons). Critical: this is a multi-tenant isolation defect. Recommend a regression test in /app/backend/tests covering all `{array_field: scalar}` queries on Couchbase.
PPA-57 | Reports — Recent Reservations shows stale data | Medium | Closed | Already fixed | Verified Closed | Reports.js sorts client-side by created_at DESC and refetches on focus / visibility change. Stays Closed. | /app/frontend/src/pages/admin/Reports.js (fetchReservations + useEffect) | Create a reservation; switch to Reports tab → it should appear at the top of Recent Reservations within 1 s of focus.
PPA-59 | Block Slots dialog — only first conflicting slot reported | Medium | Closed | Already fixed | Verified Closed | create_event_block does a two-pass create: collect ALL conflicting slots in pass 1, raise once with the full comma-separated list, only insert in pass 2 if pass 1 was empty. Stays Closed. | /app/backend/routes/event_blocks.py (create_event_block PASS 1) | POST /api/event-blocks with 3 slot_ids that all conflict on the same date — error detail must list all 3 slot labels.
PPA-64 | Building Management — slot label / status text overlap | Low | Closed | Already fixed | Verified Closed | Spot-checked: BuildingManagement.js renders the label and 'Blocked' sublabel as a flex-column stack (no longer position:absolute overlay). Tooltip = '{label} — Blocked'. Stays Closed. | /app/frontend/src/pages/admin/BuildingManagement.js (slot tile) | Open Building Management, expand a floor with at least one blocked slot — verify label + 'BLOCKED' sublabel render stacked, no overlap, at all viewport widths ≥ 768 px.

## Summary
Defect Validation 2026-04-29 — Engineering Response
Source file: 'Parking App - Defect Validation 2026 04 29.xlsx' ¦ Generated April 30, 2026
Total rows assessed | 7
Already-Closed (spot-checked) | 5
NEW failures (Confirmed real) | 2
Resolved this cycle | 2
Headline findings
PPA-70 (HIGH severity) revealed a Couchbase abstraction-layer bug that silently broke every Mongo-style array-membership query. This impacted zone enforcement (and would have impacted assigned_buildings, slot_ids, tags filters, etc.). Fix is at the abstraction layer — single-line N1QL change — and is broadly tested via the cross-feature smoke.
PPA-71 was a missing pre-flight check in /api/event-blocks. Past-date guard added; today still permitted.
Cross-feature smoke run after fixes
OK GET /api/buildings
OK GET /api/users
OK GET /api/zones
OK GET /api/event-blocks
OK GET /api/admin/reservations
OK GET /api/parking-config/{id}
OK GET /api/reports/stats
OK POST /api/event-blocks (past date) → HTTP 400 (was 200)
OK POST /api/reservations (cross-zone) → HTTP 403 (was 200)
OK PUT /api/admin/reservations/{past_id}/cancel → HTTP 400
OK GET /api/reports/stats — daily_breakdown sorted ascending