## Defect Response (2026-04-30)
Defect ID | Title | Severity | Customer Status | Our Assessment | Resolution Status | Remarks / Resolution Detail | Code Path / Files | QA Verification Steps
PPA-1 | Login - Invalid credentials shows blank page | High | Closed | Already fixed | Verified Closed | Live retest: POST /api/auth/login with wrong creds → HTTP 401 + JSON detail; LoginPage shows toast, no blank page. Stays Closed. | /app/frontend/src/pages/LoginPage.js (handleLogin) | POST a wrong-password login → expect 401 + on-page toast.
PPA-72 | Booking shows ONLY Main Building (not other buildings in user's zone) | High | New (Failed) | Confirmed real (now fixed) | Resolved | REPRODUCED on production: a user with `main_building` set AND assigned to a multi-building zone only saw their main_building in the booking dropdown. FIRST RCA WAS WRONG. I initially attributed this to the same abstraction-layer bug as PPA-70 (array-membership). That fix was necessary BUT NOT sufficient — verifying with a test user whose `main_building=None` masked the real defect. TRUE ROOT CAUSE: `/api/buildings` endpoint (routes/buildings.py, regular-user branch) restricted the query to `main_building + assigned_buildings` ONLY — zone buildings were never added to the set. So even when the abstraction returned correct zone data, the backend's first SQL filter had already trimmed the result to {main_building} before the frontend ever saw it. The frontend then intersected zone_ids with that single-building set → only main_building shown. FIX: routes/buildings.py now reads the user's zones and unions their building_ids into the user_buildings set before filtering. Admin / attendant branches unchanged. VERIFIED LIVE on Couchbase + the customer's exact scenario (user with main_building set + Main Zone with 3 buildings): dropdown now shows 'Test Building 175514', 'Main Office', 'CL Tower Makati (Main)'. Admin still sees all 19 buildings; users with no main + no zones still see all (unchanged fallback). | /app/backend/routes/buildings.py (get_buildings — regular-user branch) | 1) Set a non-admin user's main_building to building X; 2) Add that user to a zone containing buildings X, Y, Z; 3) Login as that user → /api/buildings should return [X, Y, Z]; 4) Open BookingPage → dropdown should list all three. Edge: a user with NO main, NO assigned, NO zones still sees ALL buildings (graceful fallback).
PPA-15 | Reservations by Buildings — graph name alignment | Low | Closed | Already fixed | Verified Closed | AdminDashboard BarChart YAxis is width=180 with interval=0 + ellipsis tickFormatter; Tooltip shows the full name. Stays Closed. | /app/frontend/src/pages/admin/AdminDashboard.js (BarChart YAxis) | Reload Admin Dashboard with ≥ 4 buildings of varying name lengths — labels should not overlap or clip.
PPA-57 | Recent Reservations shows stale data | Medium | Closed | Already fixed | Verified Closed | Reports.js sorts client-side by created_at DESC and refetches on focus / visibility change. Stays Closed. | /app/frontend/src/pages/admin/Reports.js (fetchReservations + useEffect) | Create a reservation; switch to Reports tab → it should appear at the top of Recent Reservations within 1 s of focus.
PPA-59 | Block Slots dialog — only first conflicting slot reported | Medium | Closed | Already fixed | Verified Closed | create_event_block does a two-pass create: collect ALL conflicting slots in pass 1, raise once with the full comma-separated list, only insert in pass 2 if pass 1 was empty. Stays Closed. | /app/backend/routes/event_blocks.py (create_event_block PASS 1) | POST /api/event-blocks with 3 slot_ids that all conflict on the same date — error detail must list all 3 slot labels.
PPA-64 | Building Management — slot label / status text overlap | Low | Closed | Already fixed | Verified Closed | BuildingManagement.js renders the label and 'Blocked' sublabel as a flex-column stack (no longer position:absolute overlay). Tooltip = '{label} — Blocked'. Stays Closed. | /app/frontend/src/pages/admin/BuildingManagement.js (slot tile) | Open Building Management, expand a floor with at least one blocked slot — verify label + 'BLOCKED' sublabel render stacked, no overlap, at all viewport widths ≥ 768 px.

## Summary
Defect Validation 2026-04-30 — Engineering Response
Source: 'Parking App - Defect Validation 2026 04 30.xlsx' ¦ Generated April 30, 2026
Total rows assessed | 6
Already-Closed (spot-checked) | 5
NEW failures (Confirmed real) | 1
Resolved this cycle | 1
Headline finding
PPA-72 was a SECOND, distinct backend bug that I initially mis-attributed to yesterday's abstraction-layer fix. /api/buildings (regular-user branch) was filtering its DB query to `main_building + assigned_buildings` only, completely ignoring the user's zone buildings. The abstraction fix from PPA-70 was necessary but not sufficient — the backend was already trimming the result before the frontend could intersect with zone_ids. The fix is now in routes/buildings.py: zone buildings are unioned into the query filter. Verified end-to-end on Couchbase: a user with main_building set + a 3-building zone now sees all 3 in the dropdown.
Two missed-symptoms in two days both relate to multi-tenant filtering. The pytest suite I keep proposing — running 12-15 critical query shapes against both DB_TYPE backends — would have caught BOTH PPA-70 and PPA-72 before customer testing.
Live cross-feature smoke (after fix)
OK GET /api/buildings → 200
OK GET /api/users → 200
OK GET /api/zones → 200
OK GET /api/event-blocks → 200
OK GET /api/admin/reservations → 200
OK GET /api/reports/stats → 200
OK GET /api/zones/user-buildings (non-admin) → 3 building_ids returned
OK POST /api/reservations cross-zone (PPA-70 retest) → 403
OK POST /api/event-blocks past-date (PPA-71 retest) → 400
OK BookingPage dropdown (PPA-72): 3 buildings shown, not just main_building