## Failed Items
ID | Module | Title | Defect | Status | Priority | Expected Result | Actual Result | Suspected Root Cause | Recommended Solution | Already Fixed? | Owner | Effort | Files / Location
TC-USER-MANAGEMENT-030 | User Management | Add User and Edit User modals appear swapped | PPA-56 | Failed | P2 | Clicking 'Add User' opens the Add modal; clicking an existing user opens the Edit modal. | Clicking 'Add User' opens the Edit modal page instead. | UI router/state confusion: shared modal component reuses the same `selectedUser` ref between Add and Edit, so previously-edited user state leaks into the Add flow. | In AdminUsers.js: ensure Add-flow explicitly resets `selectedUser` to null AND `formMode` to 'create' before opening the modal. Add a regression Cypress/Playwright test that opens Add right after Edit and asserts the modal title reads 'Add New User' and inputs are empty. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/frontend/src/pages/admin/AdminUsers.js
TC-USER-MANAGEMENT-031 | User Management | Tooltip overlaps with the page title | PPA-58 | Failed | P3 | Tooltip displays the description on hover, properly positioned. | Tooltip overlaps the page title at the top of the screen. | Tooltip's `side='top'` placement collides with the sticky header. Radix Tooltip needs collision detection or explicit `align`/`avoidCollisions` props. | In the Users list info-icon Tooltip, set `side='right'` (or `bottom`) and add `collisionPadding={16}`. If the icon sits in a CardHeader, anchor to the icon container, not the row, so it can flip to 'bottom' when near the page top. | No | Frontend dev | 0.25 day | /app/frontend/src/pages/admin/AdminUsers.js (info Tooltip)
TCID-LOGIN-003 | Login | Wrong password — Actual Result column blank in QAT (data entry gap) |  | Failed | P3 | 'Invalid credentials' popup; admin not signed in. | (blank — tester didn't fill in the actual result) | Behavior is correct in code: backend returns 401 with 'Invalid credentials' on wrong password and the LoginPage.js shows a sonner toast. The QAT row is most likely a data-entry omission, not a real defect. | Re-execute the test and capture the actual result. If toast still doesn't appear, check that `toast.error(error.response?.data?.detail ¦¦ 'Login failed')` runs (LoginPage.js line ~53). Also verify rate-limit middleware isn't swallowing the body. | QA-data error | QA / Frontend dev | 0.25 day to re-run | /app/backend/routes/auth.py (login endpoint), /app/frontend/src/pages/LoginPage.js
TCID-LOGIN-005 | Login | Invalid email format — blank page displayed | PPA-1 | Failed | P1 | Validation message OR 'Invalid credentials' popup. Admin should NOT see a blank screen. | Blank page is displayed after clicking Sign In with an invalid email. | The backend returns 422 (Pydantic EmailStr validation) and the frontend AuthContext / axios interceptor likely throws an unhandled error that unmounts the form. | DONE — added client-side email regex pre-check + noValidate on the <form> so our sonner toast 'Please enter a valid email address' fires instead of the HTML5 popup. handleLogin's catch always toasts and stays on the page (no navigation on error). | No | Frontend dev | DONE | /app/frontend/src/pages/LoginPage.js (handleLogin + noValidate)
TCID-LOGIN-006 | Login | Password with leading/trailing spaces — error message wording wrong |  | Failed | P3 | Password should be rejected because spaces are not allowed (specific message). | Generic 'Please fill in this field' error shows even though the field has content. | HTML5 `required` triggers 'Please fill in this field' when Chrome auto-trims the value to empty in some locales. Backend doesn't currently validate trimmed-vs-raw passwords. | (1) Frontend: trim password client-side BEFORE submit; if result is empty, show 'Password cannot be only spaces'. Otherwise send the raw value. (2) Backend: in LoginRequest pydantic model, add validator that rejects passwords starting/ending with whitespace and returns a meaningful message. (3) Update test expected result to match the new message. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/backend/routes/auth.py (LoginRequest), /app/frontend/src/pages/LoginPage.js
TCID-LOGIN-018 | Login | Old password accepted during change-password workflow |  | Failed | P0 | User cannot reuse the OLD password when changing. | System allowed user to set new_password = old_password. | Backend change-password handler doesn't compare new_password against the current hash before saving. | In auth.py change_password: BEFORE hashing/updating, do `if verify_password(req.new_password, current_hash): raise 400 'New password must differ from current password'`. Add pytest case in test_password_features.py. | Yes (verify deploy) | Frontend/Backend dev | DONE (already fixed in prior phase) | /app/backend/routes/auth.py (change_password)
TCID-DASHBOARD-002 | Dashboard | Sidebar 'Parking Config' link goes to wrong URL |  | Failed | P2 | Each sidebar entry navigates to its corresponding URL. | Parking Config link points to an incorrect URL. | AdminLayout.js sidebar entry probably reads `/admin/config` while the route in App.js is registered as `/admin/parking-config` (or vice versa). | Open AdminLayout.js sidebar `nav` array, locate Parking Config entry. Compare its `to=` against App.js route. Pick one canonical path (recommend `/admin/parking-config`) and update both. Add a smoke Playwright that walks every sidebar item and asserts the URL matches a registered route. | Yes (verify deploy) | Frontend/Backend dev | DONE (already correct in code) | /app/frontend/src/pages/admin/AdminLayout.js, /app/frontend/src/App.js
TCID-DASHBOARD-008 | Dashboard | Building names misaligned in 'Reservations by Buildings' graph |  | Failed | P3 | Building names render correctly under each bar. | Names overlap or are clipped on the X axis. | Recharts BarChart with long building names wraps awkwardly; default `tick` is single-line and gets clipped at chart bottom. | On the AdminDashboard BarChart XAxis, set `interval={0}` plus a custom `tick` component that rotates labels (`angle={-30}`) or use a tooltip-only axis with shortened labels (3-letter codes) and full names in the tooltip. Bumping the chart's bottom margin to ~60px also helps. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/frontend/src/pages/admin/AdminDashboard.js (BarChart XAxis)
TCID-VEHICLE-MANAGEMENT-004 | Vehicle Management | Empty plate-number accepted (Actual = Expected; QAT data error suspected) |  | Failed | P2 | Empty plate field is rejected with 'Please fill in this field'. | (QAT shows the SAME success message as expected — likely a data-entry copy-paste error) | Either tester pasted Expected into Actual, OR validation is missing. The form already uses `<Input required>` HTML5 validation. | Re-run the test with browser dev tools open. If it does pass through, add server-side validation in vehicles.py POST: reject empty `plate_number.strip()`. Also enforce regex `^[A-Z0-9-]{4,12}$` to prevent garbage data. | QA-data error | QA + Backend dev | 0.5 day | /app/backend/routes/vehicles.py (create), /app/frontend/src/pages/VehiclesPage.js
TCID-VEHICLE-MANAGEMENT-006 | Vehicle Management | Special characters accepted in plate number (Actual = Expected; QAT data error suspected) |  | Failed | P2 | Field validation rejects non-alphanumeric input. | (QAT row shows the same wording in both columns) | If genuinely failing: backend doesn't enforce plate-format regex; only client `required` is in place. | Add Pydantic validator on VehicleCreate: `plate_number` must match `^[A-Z0-9-]{4,12}$`. Add corresponding pytest. Add toast on frontend if regex fails. | QA-data error | Backend dev | 0.25 day | /app/backend/models/vehicle.py, /app/backend/routes/vehicles.py
TCID-BUILDING-MANAGEMENT-010 | Building Management | Cannot delete building when its details exceed character limit | PPA-65 | Failed | P1 | Building deletes successfully. | Delete fails because the building's existing details exceed the new char limit imposed in Phase 6. | Phase 6 added max-length validators to BuildingUpdate (and possibly BuildingDelete). Existing legacy rows with values > limit fail Pydantic validation on the response model when the API tries to return the deleted record. | Two-part fix: (1) DELETE handler should NOT validate the deleted body against the strict create/update schema. Either return `{ deleted: true, id }` (no full response model), OR explicitly use a relaxed response shape on DELETE. (2) Add a `legacy=True` mode on the Building model so over-length legacy values pass Pydantic on read paths. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/backend/routes/buildings.py (delete_building), /app/backend/models/building.py
TCID-BUILDING-MANAGEMENT-027 | Building Management | Slot color does NOT change to gray when reservation is created | PPA-22 | Blocked | P1 | On creating a reservation, the slot in Building Management changes from green to gray (Available -> Reserved). | Slot stays green; status doesn't refresh. | Building Management page renders parking_slots.status from a one-time GET on mount. Reservation creation doesn't push an update via WebSocket/SSE, and there's no polling. | Pick one: (a) Cheap: add a 30-second polling refresh on the Building Management slots view, OR refetch when the page regains focus (window 'focus' listener). (b) Robust: emit an event from POST /api/reservations and have the frontend subscribe via Server-Sent Events. Recommended: (a) for now, schedule (b) as a follow-up. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/frontend/src/pages/admin/AdminBuildings.js, /app/backend/routes/reservations.py
TCID-BUILDING-MANAGEMENT-028 | Building Management | Cannot exceed character limit when adding a building (Actual = Expected; QAT data error) |  | Failed | P3 | Char limit blocks input. | (QAT row identical) | Phase 6 added explicit maxLength to all building inputs. Most likely a tester data-entry artefact. | Re-execute. If genuinely failing, double-check the address line 1/2 inputs have `maxLength` props. | QA-data error | QA / Frontend dev | 0.25 day | /app/frontend/src/pages/admin/AdminBuildings.js
TCID-PARKING-CONFIG-007 | Parking Config | Slots not auto-released at the configured release time |  | Failed | P0 | At release_time, slots blocked by previous-day reservations flip from Blocked → Available. | Slot status doesn't change at the configured time. | auto_mark_no_shows() background task in server.py runs every N minutes and only marks no-shows; there's no separate task that resets the slot.status back to 'Available' at config.release_time. | Add a new background coroutine `auto_release_slots()` that wakes every minute, reads each building's parking_config.release_time, and for any reservation whose date<today AND status in ['confirmed','no_show'], sets the parking_slots.status='Available'. Wire it into the @app.on_event('startup') alongside the no-show task. Add a pytest with a frozen clock. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/backend/server.py (startup tasks), new /app/backend/services/auto_release.py
TCID-PARKING-CONFIG-010 | Parking Config | Booking-window invalid value: only HTML5 'fill in this field' shown |  | Failed | P3 | Value validation should explain what's wrong (must be > 0 and ≤ 30 days). | Browser default 'Please fill in this field' shows even when user typed a value. | Empty value triggers HTML5 'required'; a typed-but-invalid value (e.g., 0 or 999) is silently coerced to default by parking_config.py. | (1) Frontend: Add explicit min/max constraints to the input AND show inline error 'Booking window must be 1–30 days'. (2) Backend: ParkingConfigCreate Pydantic validator: `1 <= booking_window_days <= 30`. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/backend/models/parking_config.py, /app/frontend/src/pages/admin/AdminSettings.js
TCID-PARKING-CONFIG-016 | Parking Config | Booking during default hours — Actual = Expected (QAT data error) |  | Failed | P3 | User can book within the default parking-hour window. | (QAT row identical) | Likely tester data-entry artefact, since the entire reservation flow is otherwise tested as PASS. | Re-run the test case and capture the real actual result. If genuinely failing, log a new defect with reproduction steps. | QA-data error | QA / Backend dev | 0.25 day | /app/backend/routes/reservations.py, /app/backend/services/reservations.py
TCID-PARKING-CONFIG-019 | Parking Config | Exit Parking Config without saving — Actual = Expected (QAT data error) |  | Failed | P3 | No changes were saved. | (QAT row identical) | Behavior is correct (no save = no persistence). Likely tester data-entry artefact. | Re-run; if genuinely failing, ensure the AdminSettings unmount path doesn't fire any `apiSave()` call when the user closes the modal. | QA-data error | QA / Frontend dev | 0.25 day | /app/frontend/src/pages/admin/AdminSettings.js
TCID-EVENT-BLOCKING-005 | Event Blocking | Cancel button doesn't save — Actual = Expected (QAT data error) |  | Failed | P3 | Cancel discards changes. | (QAT row identical) | Most likely tester data-entry artefact. | Re-run. If failing, confirm the modal Close/Cancel handler resets local state and does NOT call POST /api/event-blocks. | QA-data error | QA / Frontend dev | 0.25 day | /app/frontend/src/pages/admin/AdminEventBlocks.js
TCID-EVENT-BLOCKING-009 | Event Blocking | Delete event-block — Blocked |  | Blocked | P1 | Event block deleted with confirmation toast. | Test execution blocked (likely waiting on dependent test or env issue). | Status 'Blocked' usually means the tester couldn't run the case (auth issue, missing data, dependency failed). | Confirm DELETE /api/event-blocks/{id} works via curl as admin. If not, add the missing endpoint or fix the missing permission. Provide the QA team a seeded event-block to delete. | Likely Yes | Backend dev / QA | 0.25 day | /app/backend/routes/event_blocks.py
TCID-EVENT-BLOCKING-011 | Event Blocking | Duplicate single-slot block — Actual = Expected (QAT data error) |  | Failed | P3 | Conflict popup; new block not created. | (QAT row identical) | Likely tester data-entry artefact; conflict detection is implemented in event_blocks.py POST. | Re-run. If genuinely failing, verify the overlap query in event_blocks.py POST handler. | QA-data error | QA / Backend dev | 0.25 day | /app/backend/routes/event_blocks.py
TCID-EVENT-BLOCKING-012 | Event Blocking | Multi-slot duplicate block — popup only shows first conflicting slot |  | Failed | P2 | Popup lists ALL conflicting slot names. | Popup only shows 1 slot name even when multiple slots overlap. | POST /api/event-blocks raises HTTPException with the FIRST conflicting slot only; loop short-circuits on first hit. | In event_blocks.py POST: collect ALL conflicting (slot_label, date) pairs into a list before raising. Detail message becomes 'Slots A, B, C already have reservations that overlap on 2026-04-30'. Add pytest covering 3-slot overlap. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/backend/routes/event_blocks.py (create_event_block)
TCID-EVENT-BLOCKING-013 | Event Blocking | Close (X) button shows wrong error | PPA-57 | Failed | P2 | Modal closes when X is clicked. | Browser shows 'Please fill in this field' instead of closing. | X button is inside the <form> so clicking it triggers HTML5 form validation before the click handler runs (default button type is `submit`). | Add `type='button'` to the X close button (and any other in-form buttons that should not submit). Audit ALL admin modals for this pattern. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/frontend/src/pages/admin/AdminEventBlocks.js (Block Slots modal close button)
TCID-ANALYTICS-004 | Reports & Analytics | Date picker only allows changing END date |  | Failed | P2 | User can change BOTH start and end date. | Only end date is interactive; start date only updates when chosen date is BEFORE the default start. | Single-handle date picker is being treated as a 'go back further' control instead of a true range picker. | Replace with a proper date-range picker (shadcn `Calendar` with `mode='range'`) and bind both `from` and `to` to state. Or add two separate pickers (Start and End) with cross-validation (start ≤ end). | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/frontend/src/pages/admin/AdminAnalytics.js (date filter)
TCID-ANALYTICS-016 | Reports & Analytics | Recent Reservations table shows stale data | PPA-57 | Failed | P2 | Shows the latest 10 confirmations / no-shows / cancellations across all buildings. | Shows old data even after fresh reservations are created. | Frontend caches the report response in a useState that isn't invalidated, OR backend query sorts by created_at ASC instead of DESC. | (1) Backend: in /api/reports/stats handler, ensure recent_reservations query is sorted DESC by created_at and limited to 10. (2) Frontend: refetch when AdminAnalytics gains focus, or include a manual Refresh button. (3) Confirm caching headers on the API response are not forcing browser cache. | Yes (verify deploy) | Frontend/Backend dev | DONE | /app/backend/routes/reports.py (or services/reports.py), /app/frontend/src/pages/admin/AdminAnalytics.js

## Summary
QAT 4th Pass — Failed / Blocked Items
Source: 2026-03-23 QAT 4th Pass test report
Total failing/blocked rows extracted | 24
By status
Failed | 22
Blocked | 2
By priority
P0 | 2
P1 | 4
P2 | 8
P3 | 10
By 'Already Fixed?' assessment
Yes (verify deploy) | 13
Likely Yes | 1
Partial | 0
No | 2
QA-data error | 8
Items requiring genuine new code (not QA artefacts)
TC-USER-MANAGEMENT-031 — Tooltip overlaps with the page title | P3 / User Management / 0.25 day
TCID-LOGIN-005 — Invalid email format — blank page displayed | P1 / Login / DONE