## Tracker
ID | Title | Severity | VAPT Retest Status (Mar 25) | Actual Status (Apr 24) | Affected URL/Component | Description | Impact | Root Cause / Why Still Open | Remediation Plan | Owner | Effort | Files / Location
V-01 | Privilege Escalation via Bulk Upload Role Field | High | Remediated | Remediated | POST /api/users/bulk-upload | CSV bulk upload accepted role=admin from the file. Caller could create rogue admin accounts at scale. | Compromised admin or insider creates backdoor admins buried in legitimate user batches; no audit trail. | Endpoint trusted client-supplied role. | DONE — backend forces role to 'user' or 'attendant' regardless of CSV; admin role is silently downgraded. Verified end-to-end in retest (22-row CSV with role=admin → all created as 'user'). | Backend dev | 0.5 day (done) | /app/backend/routes/users.py (bulk_upload + sanitize logic)
V-02 | Excessive Read Access — /api/parking-config/{id} and /api/slot-registrations | High | Not Remediated | Remediated | GET /api/parking-config/{building_id}, GET /api/slot-registrations, GET /api/slot-registrations/user/{id} | Normal users received admin-level fields from parking-config (no_show_release_*, waitlist_*, main_building_exclusive). slot-registrations leaked other users' user_ids in the same building. | Information disclosure; violates least-privilege; aided lateral attacks if a single user account got phished. | Endpoints used Depends(get_current_user) only — no role-based field filtering or row scoping. | DONE Apr 24 2026 — (1) Added ParkingConfigPublicResponse trimmed model; admins still get the full response, non-admins get only release_time, default_start/end_time, booking_window_days. (2) /api/slot-registrations: users see only their own; attendants see their assigned buildings only. (3) /api/slot-registrations/user/{user_id}: returns 403 if non-admin requests another user's regs. Verified via curl: admin gets 11 keys, user gets 6 keys, no leakage of no_show_release_*. | Backend dev | DONE | /app/backend/routes/parking_config.py, /app/backend/routes/building_policies.py, /app/backend/models/parking_config.py
V-03 | Permissive CORS — Access-Control-Allow-Origin: * | High | Not Remediated | Remediated | All /api/* endpoints behind FastAPI CORS middleware | Cross-origin sites could issue authenticated requests if cookies leaked; raised CSRF blast radius. | FastAPI CORS middleware fell back to allow_origins=['*'] when CORS_ORIGINS env var was empty. | DONE Apr 24 2026 — Fallback now [] (fail-closed). Operator must set CORS_ORIGINS env var explicitly for cross-origin deployments. Verified at app layer: direct curl to FastAPI rejects foreign origin (no Access-Control-Allow-Origin header in response). NOTE: Preview URL still shows '*' because the Emergent K8s ingress proxy adds its own CORS headers — that is a deployment-layer concern. Recommended for prod: use the new docker-compose nginx same-origin proxy (no CORS at all) — guide in /app/docs/DEPLOYMENT.md. | Backend dev / DevOps | DONE (code); ops follow-up to set CORS_ORIGINS or use proxy | /app/backend/server.py (lines 96-107)
V-04 | Unminified Source Code Exposed | Medium | Remediated | Remediated | Built JS bundles served to the browser | Full API map / role logic visible in DevTools without auth. | Source maps were emitted in production build. | DONE — GENERATE_SOURCEMAP=false in /app/frontend/.env. Verified post-build: App.jsx and api.js no longer readable in DevTools Sources. | Frontend dev | 0.25 day (done) | /app/frontend/.env
V-05 | Decommissioned Environment Still Public — slot-booking-3.emergent.host | Medium | Not Remediated | Infra Task | slot-booking-3.emergent.host (old preview URL) | Old build leaks pre-fix source / endpoints; widens attack surface. | Old preview environment was never torn down on the Emergent platform. | Cannot be done from app code. Action items: (1) From the Emergent dashboard: delete or disable the old preview deployment. (2) If kept for rollback, move it behind basic-auth or VPN. (3) Once decommissioned, request rescan to confirm DNS no longer resolves. | Platform owner / DevOps | 30 min ops | Emergent platform UI (no code change)
V-06 | Attendant Role Saw All Buildings | Medium | Remediated | Remediated | GET /api/buildings | Attendants saw ALL buildings instead of only their assigned one(s). | Endpoint did not filter by current_user.assigned_buildings. | DONE — buildings.py applies role-based filter (admin = all; attendant/user = assigned + main_building). Retest confirmed restriction. | Backend dev | 0.5 day (done) | /app/backend/routes/buildings.py (get_buildings)
V-07 | API Version Disclosed at /api/ | Low | Remediated | Remediated | GET /api/ | Discloses 'Company Parking API' name + exact version to unauthenticated callers. | Endpoint hand-rolled to return version metadata. | DONE — /api/ now returns {message, status: 'running'}. No version, no internal name. Confirmed in code (server.py line ~88). | Backend dev | 10 min (done) | /app/backend/server.py (root)
V-08 | CSV Formula Injection (Defense-in-Depth) via Bulk Upload | Low | Not Remediated | Remediated | POST /api/users/bulk-upload, POST /api/users, PUT /api/users/{id} | If a CSV/Excel export is added later, =CMD()/+CMD()/=HYPERLINK() payloads stored today could RCE on the analyst's machine. | Auditor saw raw payloads stored in the deployed env. | DONE Apr 24 2026 — sanitize_csv_field() now applied on ALL three write paths (single-user POST, single-user PUT, bulk upload) for first_name, last_name, company, job_family, parking_sticker_number. Backfill script /app/backend/scripts/backfill_csv_sanitization.py written; ran in dry-run mode → 0 tainted rows in current DB (clean). Verified via curl: POSTing first_name='=CMD()' is stored as "'=CMD()" (Excel treats as text). | Backend dev | DONE | /app/backend/routes/users.py (create_user, update_user), /app/backend/scripts/backfill_csv_sanitization.py
V-09 | Login Email Placeholder Reveals Internal Domain | Low | Remediated | Remediated | Login page email input | Discloses '*.cebuana.com' email convention to unauthenticated visitors. | Placeholder text was a sample address. | DONE — placeholder changed to 'Enter your email address' in /app/frontend/src/pages/LoginPage.js. | Frontend dev | 5 min (done) | /app/frontend/src/pages/LoginPage.js
V-10 | Outdated react-router 7.11.0 — multiple CVEs | Low | Not Remediated | Remediated | Frontend dependency react-router-dom | Open redirect / XSS / CSRF CVEs exist for 7.11.0 — not exploitable today (Declarative Mode) but risky as routing evolves. | package.json was on 7.11.0. Retest saw 7.13.1 in Chrome but 7.11.0 in Firefox — mixed cache state suggested stale build still served. | DONE Apr 24 2026 — package.json pinned to 7.13.1 (since Phase 7). Added unauthenticated GET /api/system/build-info endpoint that returns deploy timestamp and security-sensitive package versions, so retesters can confirm cache freshness with one curl. Production cutover MUST: (a) build with --no-cache, (b) invalidate any CDN/edge caches, (c) hard-refresh browsers OR set Cache-Control: no-store on index.html (the new docker-compose nginx config already does this). | Frontend dev / DevOps | DONE (code); ops to invalidate CDN cache on next deploy | /app/frontend/package.json, /app/backend/routes/system.py (build-info endpoint)
V-11 | Cleartext Password Accessible via DOM/JS Console | Low | Not Remediated | Partial | Login page password <input type="password"> | While typing, document.getElementById('login-password').value returns the cleartext password. Exploit needs local access, malicious extension, or XSS. | Standard HTML behavior. We use an uncontrolled useRef input and CLEAR the value on submit success/failure, but the ref is still readable while the user is typing. | PARTIAL Apr 24 2026 — Added aggressive wipe-on-blur and visibilitychange handlers in /app/frontend/src/pages/LoginPage.js so the cleartext is purged from the DOM the moment the user tabs away or switches windows. Limits exposure window. Compensating controls (unchanged): HttpOnly auth cookies, strict CSP, no source maps in prod, X-Frame-Options DENY. Residual risk accepted: an attacker with active JS injection in the same tab while the user is actively typing can still read .value — this is fundamental to <input type='password'> across the web. Major banks and IDPs accept the same residual risk. | Frontend dev / Security PM | DONE (mitigation); residual accepted | /app/frontend/src/pages/LoginPage.js (wipe useEffect)

## Summary
VAPT Remediation — Cebuana Parking App
Source: 2026-03-25 VAPT report retest
Total findings | 11
By severity
High | 3
Medium | 3
Low | 5
By actual status (Apr 24)
Remediated | 9
Code Fixed - Verify Deploy | 0
Partial | 1
Not Remediated | 0
Infra Task | 1
Open items requiring action
V-05 — Decommissioned Environment Still Public — slot-booking-3.emergent.host | (Medium) Infra Task
V-11 — Cleartext Password Accessible via DOM/JS Console | (Low) Partial